## WBS
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | Make Your Life Easy
PROJECT MANAGER | Parvej Alam Ansari
COMPANY NAME | E-commerce LTD
DATE | 2023-11-06 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Parvej Alam Ansari | 2023-11-01 | 2023-11-02 | 1 | 100%
1.1.1 | Project Charter Revisions | Parvej Alam Ansari | 2023-11-03 | 2023-11-04 | 1 | 100%
1.4 | Stakeholders | Parvej Alam Ansari | 2023-11-05 | 2023-11-07 | 2 | 70%
1.5 | Guidelines | Parvej Alam Ansari | 2023-11-08 | 2023-11-10 | 2 | 60%
1.6 | Project Initiation | Parvej Alam Ansari | 2023-11-11 | 2023-11-12 | 1 | 50%
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Team | 2023-11-13 | 2023-11-15 | 2 | 5%
2.2 | Budget | Finance | 2023-11-16 | 2023-11-18 | 2 | 30%
2.3 | Communication Plan | Marketing | 2023-11-19 | 2023-11-20 | 1 | 10%
2.4 | Risk Management | Stefano Ricci | 2023-11-08 | 2023-11-09 | 1 | 0%
3 | Project Launch & Execution | Team | 2023-11-11 | 2023-11-14 | 3 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Team | 2023-11-15 | 2023-11-30 | 15 | 0%
4.2 | Quality Deliverables | Team | 2023-11-27 | 2023-12-31 | 34 | 0%
4.3 | Effort & Cost Tracking | Team | 2023-11-30 | 2024-01-30 | 61 | 0%
4.4 | Project Performance | Team | 2024-04-04 | 2024-05-31 | 57 | 0%
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])