## Sheet1
Activity | Predecessor | Duration
Analysis |  | 6
Design | Analysis | 2
Development | Design | 40
Training | Design | 20
Documentation | Design | 9
Manual Testing | Development | 4
Automated Testing | Training | 15
Pilot | Training, Documentation | 5
Deply | Manual Testing, Automated Testing, Pilot, Training | 3
104