## Sheet1
Comminucations Plan [Date: 08/11/2023]
What | Who-sender | Who-Reciever | When | How/Where | Why
Sponsor 1:1 Meeting | Juan | Sandra and Morgan | Friday 10 to 10:30 AM | Morgans Office | Update the project sponsor and discuss help wanted
Change Control Board | Sandra | All key steakholders | Bimonthly on Tue from 9 to 10 AM | Back Conference Room | Review change requests and approve or dissaprove it
Weekly Project Status Report | Sarah | Sandra and department lead | Tuesday | MS Excel in Sharepoint | Provide an overview of key project status
Gift Packet Development | Michael | Project team and Sandra | March 15 from 1 to 3 PM | Main Conference Room | Assemble gift baskets
Vendor Source Selection | Sarah | Ramesh, Juan and Sandra | From 11 to 12 PM | Teams Meeting | finalize catering and all related contracts.
AV/IT Support Selection | Sophia | Juan, Sandra and Team | February 10 From 9 to 9:30 AM | Conference Room | Finalize av/it preparations and determine if external help is needed
Weekly project status meeting | Juan | Project team | Tuesday From 10 to 10:30 AM | Conference Room | Review status, discuss open issues and risks and review deliverables