## Potential Solution
Resource Breakdown Structure/Resource Management PlanResource Breakdown Structure/Resource Management Plan Project Name: Semi-Annual Investor Workshop Date: November 08, 2023
Resource Breakdown Structure/Resource Management Plan Project Name: Interior Design by Harmony Date: 08 November, 2023
| WBS Identifier # | Work Package | Internal Personal Required |  | External Personnel Required |  | Software and Tools |  | Supplies Required |  | Equipment Required |  | Furniture and Lighting | Other 2 |  | Start Date | Finish Date
|  |  | Name | Amount | Name | Amount | Name | Amount | Name | Amount | Name | Amount
| 1.1.1 | Project Plan |  |  | Extended Team Requirements | 3630 | [9 empty] | 2023-10-01 | 2023-10-04
| 1.1.2 | Budget Plan | Core Team Requirments | 28900 | [11 empty] | 2023-10-05 | 2023-10-09
| 1.1.3 | Resource Plan | [13 empty] | 2023-10-10 | 2023-10-14
| 1.2.1 | Design Concept | [13 empty] | 2023-10-15 | 2023-10-19
| 1.2.2 | Furniture and Materials Selection | [6 empty] | Atendees Packages | 26750 | [5 empty] | 2023-10-20 | 2023-10-22
| 1.2.3 | Lighting Plan | [13 empty] | 2023-10-20
| 1.3.1 | Furniture and Materials Purchasing | [6 empty] | Catering | 20000 | [5 empty] | 2023-10-22
| 1.3.2 | Installation |  |  |  |  | Technology | 600 |  |  | Venue | 12375 |  |  |  | 2023-10-24
| 1.3.3 | Final Walkthrough | [11 empty] | Other | 2000 | 2023-10-29
| Totals | 94255 | 28900 |  | 3630 |  | 600 |  | 46750 |  | 12375 |  | 0 | 2000
| Total Project Funding |  | 94255
| Contingency Reserve |  | 9425.5

## Challenges
Step | Potential Challenges